## Sheet1
County Timeline for Compensation Agreement Approval*
Timeline | Process | Action
Week 1 | Staff Review | Staff reviews agreement to ensure that key points are addressed:
1. Does the agreement describe the intended use of the property?
2. Are taxing entities determined either on a project area or agency-wide basis?
3. Is there a definition of "Net Unrestricted Proceeds?"
4. Is a requirement to prepare a 52201 report and public noticing requirements included?
5. Is a notice against title included?
6. How are funds to be distributed? Escrow?
Weeks 2 and 3 | ATC Review | Agreement sent to County Auditor Tax Controller (ATC) for review.
Weeks 2 and 3 | County Counsel Review | Agreement sent to County Counsel for review
Weeks 4 through 6 | Discussions with City | If necessary, sent back to City to make changes.
Meet with City to discuss changes.
| County Counsel Review | Send to County Counsel once changes are made after City discussions.
| Board Item Preparation and Review | 4. Board Item drafted
Weeks 7-12 |  | Board item routed through County Departments for review.
Weeks 13 and 14 | Approval of Agreement | Board of Supervisors Meeting for approval. After approval the clerk will provide final signed agreements.
*This schedule is subject to change based on the nature of the agreement.